## Sheet1
Week | Milestone: High Level Goal | Weekly Demo Task (30 second video)
1 | Kickoff | Kickoff (present plan)
2 | Continous Deployment | Continous Deployment
3 | Setup GCP | GCP Skeleton Project
4 | Big Query Setup | Big Query Integration
5 | Big Query Modeling and Prediction | Big Query Prediction
6 | AutoML Setup | AutoML Prediction
7 | Creation of Multiple Environments | Staging Environment
8 | Integrate API | Computer Vision API
9 | Stackdriver Setup | Monitoring
10 | Finish MVP | MVP